## Test Cases
Test Case ID | Test Scenario | Steps | Expected Result | Status
TC-001 | Verify homepage loads properly | Open browser and navigate to Pahona.org | Homepage should load correctly | Pending
TC-002 | Verify user registration | Click 'Sign Up', enter details, submit | User should be registered and logged in | Pending
TC-003 | Verify login functionality | Enter valid credentials and click 'Login' | User should be logged in | Pending
TC-004 | Verify forgot password feature | Click 'Forgot Password', enter email | Password reset link should be sent | Pending
TC-005 | Verify website layout consistency | Open different pages | UI should be consistent across pages | Pending
TC-006 | Test mobile responsiveness | Open site on mobile devices | Site should be responsive | Pending
TC-007 | Check for broken links | Click all hyperlinks | No broken links should be found | Pending
TC-008 | Page load speed | Open homepage | Page should load within 3 seconds | Pending
TC-009 | Stress testing | Simulate high traffic | Site should not crash or degrade significantly | Pending
TC-010 | SQL Injection Prevention | Enter SQL script in login form | Input should be sanitized and rejected | Pending
TC-011 | XSS Attack Prevention | Enter script in input fields | Site should block script execution | Pending
TC-012 | Browser Compatibility | Open site in different browsers | Site should work as expected on all tested browsers | Pending
TC-013 | Mobile OS Compatibility | Open site on iOS & Android | Site should function correctly on both OS platforms | Pending

## Test Plan
Test Plan for Pahona.org
1. Introduction
Project Name: | Pahona.org Testing
Tested By: | QA Team
Test Start Date: | [Insert Date]
Test End Date: | [Insert Date]
Test Objective: | Ensure that Pahona.org is functional, secure, and user-friendly across various devices and browsers.
2. Scope
Functional Testing
UI/UX Testing
Performance Testing
Security Testing
Compatibility Testing (Browsers & Devices)
Mobile Responsiveness Testing
API Testing (if applicable)
3. Test Approach
Manual Testing: Basic functionalities and UI.
Automated Testing: Regression and performance testing.
Exploratory Testing: Identifying unexpected behaviors and edge cases.
4. Test Environment
Operating Systems: | Windows, macOS, Linux
Browsers: | Chrome, Firefox, Safari, Edge
Devices: | Desktop, Tablet, Mobile (Android & iOS)
Test Data: | Dummy user accounts, sample data sets
6. Defect Management
Bug Reporting Tool: | Jira/Trello/Excel
Bug Priority Levels:
Critical: | Site crash, data loss
High: | Login failure, broken features
Medium: | UI issues, minor functionality problems
Low: | Typos, small layout misalignments
7. Test Exit Criteria
All critical bugs fixed.
Functional requirements met.
UI and security issues resolved.
8. Test Deliverables
Test Plan Document
Test Cases
Bug Reports
Test Summary Report